DIGITAL LIBRARY INITIATOR

Digital Library Transformation Project Proposal

Submitted to: Secretary, College Education & Literacy Department
Client Institution: SMB Fatima Jinnah Government Girls Degree College (GGDC)
Consultant: Digital Library Initiator
Project Duration: Six Months
Proposed Budget: PKR 10,000,000 (PKR 1 Crore)
Project Title: Transformation of the Manual College Library into a Digital and Automated Library

1. Executive Summary

Digital Library Initiator proposes to transform the manual library of SMB Fatima Jinnah GGDC into an automated, searchable and user-friendly digital library.

The library has a collection of 4,723 books. Manual cataloguing, circulation records and stock management can make it difficult to locate books, track availability and prepare accurate reports. This project will introduce a library management system, electronic catalogue, barcode-based circulation, staff training, inventory controls and secure backup procedures.

The project will be completed through a six-month phased implementation strategy. The proposed budget ceiling is PKR 10 million, subject to institutional approval, procurement rules, site assessment and verified vendor quotations.

The project's central objective is to improve library services, support students and faculty, strengthen collection management and establish a sustainable digital foundation for the college.

2. Background and Need

The existing manual library system requires organized records and staff time for routine activities such as book searches, issue and return transactions, overdue tracking and stock verification.

A digital library management system can improve these processes through:

- Electronic catalogue creation for 4,723 books.

- Faster searches by title, author, subject and other available metadata.

- Automated issue, return and renewal records.

- Barcode-based identification and stock control.

- More accurate circulation and collection reports.

- Better discovery of resources by students and faculty.

- Secure storage, backup and recovery of library data.

The project will prioritize digitizing bibliographic records and automating library operations. Full-text scanning and online distribution of copyrighted books are not included unless appropriate permissions are obtained.

3. Project Objectives

- Catalogue and verify the collection of 4,723 books.

- Implement a suitable library management system.

- Establish a searchable Online Public Access Catalogue (OPAC).

- Introduce barcode-based circulation and inventory tracking.

- Reduce dependence on manual registers for routine operations.

- Train library staff in software operation, reporting and troubleshooting.

- Improve student and faculty access to library resources.

- Establish documented data protection, backup and recovery procedures.

- Complete implementation and formal handover within six months.

- Provide a sustainable support and maintenance arrangement.

4. Scope of Work and Deliverables

| Workstream | Deliverables |
| --- | --- |
| Requirements assessment | Site survey, stakeholder interviews, workflow assessment and approved project plan |
| Infrastructure | Computers, peripherals, network and power-protection equipment according to the approved specification |
| Software | Configured library management system, user accounts, circulation rules and reporting |
| Catalogue | Searchable records for the 4,723-book collection, with documented exceptions |
| Barcode system | Book labels, barcode scanning and circulation workflows |
| OPAC | Search interface for students and faculty on approved devices and networks |
| Training | Staff workshops, user guides and standard operating procedures |
| Testing | Catalogue checks, circulation testing, security checks and user acceptance testing |
| Handover | System documentation, asset register, data export, backup procedures and support plan |

5. Six-Month Implementation Strategy

Month 1 — Assessment and Planning

Activities

- Hold a project kick-off meeting.

- Review existing accession registers and catalogue records.

- Conduct a physical and infrastructure assessment.

- Interview the librarian, principal, IT staff and administration.

- Identify data-quality problems, missing books and duplicate records.

- Finalize technical requirements and procurement specifications.

- Approve the project charter, budget baseline and risk register.

Deliverables: Requirements report, approved implementation plan, site assessment and procurement specifications.

Month 2 — Infrastructure and System Configuration

Activities

- Procure approved hardware and software.

- Install equipment and configure the selected system.

- Establish user roles and circulation policies.

- Prepare catalogue templates and classification rules.

- Configure the public catalogue and restricted staff functions.

- Test security permissions and backup arrangements.

Deliverables: Installed infrastructure, configured test system and approved catalogue template.

Month 3 — Pilot and First Catalogue Batch

Activities

- Clean and enter the first batch of book records.

- Apply and test barcode labels.

- Test book searches and availability displays.

- Pilot issue, return and renewal processes.

- Train designated staff in basic system operation.

- Review data quality and correct early problems.

Planning target: Approximately 1,600 books processed, subject to the results of the initial catalogue assessment.

Deliverables: Pilot report, first catalogue batch and initial staff training.

Month 4 — Second Catalogue Batch

Activities

- Continue catalogue creation and barcode processing.

- Reconcile electronic records with accession registers.

- Review classification and subject metadata.

- Conduct progress meetings and cost reviews.

- Address problems identified during the pilot.

- Train staff in reports and inventory functions.

Planning target: Approximately 3,200 cumulative books processed.

Deliverables: Interim catalogue report, quality-assurance results and updated risk register.

Month 5 — Completion and Testing

Activities

- Process the remaining books.

- Document missing, damaged, duplicate and incomplete records.

- Test OPAC searches and circulation workflows.

- Conduct user acceptance testing with the college team.

- Test backup restoration and access permissions.

- Complete staff training and resolve critical defects.

Deliverables: Collection reconciliation report, user acceptance testing results and go-live readiness recommendation.

Month 6 — Go-Live and Handover

Activities

- Launch the approved digital library service.

- Monitor system performance and user feedback.

- Resolve priority issues.

- Provide final training and technical documentation.

- Transfer approved administrative access securely.

- Submit final financial and implementation reports.

- Agree on ongoing support and maintenance.

Deliverables: Operational digital library, final handover report, support plan and formal client acceptance.

The monthly book-processing figures are planning targets, not guaranteed counts. The actual schedule will be adjusted after sampling the collection and reviewing record quality.

6. SWOT Analysis

| Strengths | Weaknesses |
| --- | --- |
| Clearly identified collection of 4,723 books | Existing manual records may contain incomplete information |
| Librarian-led project ownership | Staff may require additional digital skills training |
| Defined six-month delivery target | Initial equipment and configuration investment |
| Potential for improved reporting and circulation | Data entry requires sustained quality control |

| Opportunities | Threats |
| --- | --- |
| Improved student access and book discovery | Procurement and delivery delays |
| Future integration of e-resources | Power, network or equipment failures |
| Better collection statistics for management | Data loss or unauthorized access |
| Potential expansion to other institutional libraries | Resistance to changing established workflows |

7. Risk Management

| Risk | Mitigation | Responsible party |
| --- | --- | --- |
| Incomplete book records | Sample the collection and maintain an exception register | Librarian and consultant |
| Procurement delays | Approve specifications early and monitor procurement milestones | Department and procurement team |
| Catalogue errors | Use metadata rules and conduct sample checks | Librarian and data-entry team |
| Staff resistance | Provide hands-on training and involve staff in testing | College project lead |
| Equipment or power failure | Use appropriate power protection, backups and warranty support | IT representative |
| Data breach | Restrict access, secure accounts and separate public catalogue information from borrower records | IT representative |
| Budget overrun | Use written change requests and monthly financial reporting | Sponsor and finance team |
| Delayed completion | Monitor weekly progress and escalate schedule risks | Project manager |

8. Proposed Budget

| Budget category | Estimated cost (PKR) |
| --- | --- |
| Computers, workstations and peripherals | 2,000,000 |
| Server or hosting, networking, storage and power protection | 1,000,000 |
| Library software configuration, licensing and customization | 1,500,000 |
| Catalogue preparation, data entry and barcode processing | 2,000,000 |
| Implementation, testing and project management | 1,200,000 |
| Staff training and documentation | 500,000 |
| Security, backup and quality assurance | 400,000 |
| Initial support and post-launch assistance | 500,000 |
| Controlled contingency reserve | 900,000 |
| Total proposed budget ceiling | 10,000,000 |

Financial clarification: These figures are preliminary planning allowances, not verified market quotations. The final budget must be supported by a detailed bill of quantities, competitive vendor quotations and applicable procurement requirements. Taxes, recurring subscriptions, hosting renewals and any major civil or electrical works must be explicitly confirmed.

The contingency reserve may only be used with written authorization.

9. Project Governance

The proposed project team will include:

- Project Sponsor: Authorized departmental representative.

- Institutional Lead: Principal or nominated college representative.

- Library Lead: College Librarian.

- Technical Lead: IT or systems representative.

- Financial Lead: Finance and procurement representative.

- Consultant: Digital Library Initiator Project Manager.

- Users: Selected faculty and student representatives.

A weekly working review and monthly steering meeting will track progress, expenditure, risks, decisions and upcoming milestones.

Changes to approved cost, scope or schedule must be documented and approved before implementation.

10. Key Performance Indicators

| Indicator | Proposed acceptance measure |
| --- | --- |
| Catalogue coverage | All 4,723 books processed or accounted for in a documented exception register |
| Metadata quality | At least 95% compliance in an agreed sample of required catalogue fields |
| Circulation | Issue, return and renewal workflows successfully tested |
| Search functionality | OPAC searches tested on approved devices and networks |
| Training | Designated staff complete practical training |
| Security | Role permissions and backup restoration tested |
| Financial control | Monthly actual-versus-forecast expenditure reporting |
| Delivery | Go-live and handover targeted within six months |

11. Client Satisfaction Plan

Digital Library Initiator will use the following measures to support client satisfaction:

- Assign a named project manager and clear escalation contact.

- Provide weekly progress updates and monthly steering reports.

- Demonstrate the system at pilot, testing and launch stages.

- Maintain an action register containing decisions, owners and deadlines.

- Obtain client approval at important project milestones.

- Explain cost assumptions and exclusions transparently.

- Provide documentation and catalogue data in an agreed exportable format.

- Conduct staff feedback sessions before and after launch.

- Test backup restoration and document recovery procedures.

- Provide a written support arrangement with agreed response targets.

12. Proposed Payment Schedule

| Milestone | Proposed share |
| --- | --- |
| Contract and approved project charter | 10% |
| Design and infrastructure acceptance | 20% |
| Configured system and pilot catalogue | 20% |
| Interim catalogue and staff training | 20% |
| User acceptance and collection reconciliation | 20% |
| Final handover and acceptance | 10% |
| Total | 100% |

Payments will be subject to the approved contract, procurement rules, evidence of deliverables and authorized milestone acceptance.

13. Exclusions and Dependencies

- Full-text digitization of copyrighted books is excluded unless permissions are obtained.

- Ongoing subscription and hosting costs beyond the agreed contract period must be identified separately.

- Major building alterations or electrical upgrades require separate assessment and approval.

- The college must provide authorized access to existing registers, collection areas and relevant staff.

- Implementation depends on timely procurement decisions and stakeholder approvals.

14. Conclusion

Digital Library Initiator recommends a phased, measurable and client-focused transformation of SMB Fatima Jinnah GGDC's manual library. The six-month plan will establish an automated foundation for managing the 4,723-book collection while emphasizing data quality, staff capability, financial transparency and sustainable service delivery.

We respectfully submit this proposal for review and approval.

Submitted by:
Digital Library Initiator
Digital Library Transformation Consultant

Approval section

| Approving authority | Name and designation | Signature/date |
| --- | --- | --- |
| Departmental Sponsor |  |  |
| College Principal or Nominee |  |  |
| College Librarian |  |  |
| Digital Library Initiator Project Lead |  |  |